Meeting Info

meeting_title: Smart Building IoT System - Requirements Review; date: 2026-04-02; time: 2:00 PM; location: Virtual - Microsoft Teams; facilitator: Noura Al-Otaibi

Attendees

name: Noura Al-Otaibi, role: Project Manager; name: Ibrahim Qasim, role: IoT Solutions Architect; name: Fatima Al-Zahrani, role: Business Analyst; name: James Wilson, role: Vendor Technical Representative; name: Abdullah Nouri, role: Facilities Manager

Agenda

Review of draft requirements document; Vendor hardware compatibility discussion; Energy management module scope confirmation; Data privacy and compliance requirements; Risk review and mitigation strategies; Next steps and timeline confirmation

Discussion Summary

Noura initiated the session with a review of the draft requirements document prepared by Fatima. Ibrahim noted that three of the proposed sensor types are incompatible with the current building network infrastructure and would necessitate additional cabling work, estimated at three weeks. James confirmed that the vendor can supply compatible sensor alternatives, but the lead time is six weeks from order placement. Abdullah emphasized that energy reporting must align with the Saudi Green Building Standard requirements and requested this be added as a mandatory functional requirement. The team addressed data privacy concerns related to occupancy tracking sensors and agreed that only anonymized, aggregated data would be collected in common areas. Fatima highlighted that the current requirements document does not cover system behavior during network outages and requested Ibrahim to define the offline fallback behavior prior to the next meeting.

Decisions

Alternative sensor types from vendor approved subject to cost confirmation; Energy reporting module must comply with Saudi Green Building Standard; Occupancy tracking limited to anonymized aggregated data in common areas only; Offline fallback behavior to be defined and added to requirements before sign-off; Procurement process to start immediately to account for 6-week hardware lead time

Action Items

task: Update requirements document with Saudi Green Building Standard alignment, owner: Fatima Al-Zahrani, due_date: 2026-04-09, status: open; task: Define system offline fallback behavior specification, owner: Ibrahim Qasim, due_date: 2026-04-07, status: open; task: Submit hardware quotation for alternative sensor types, owner: James Wilson, due_date: 2026-04-06, status: open; task: Initiate procurement approval process for hardware order, owner: Noura Al-Otaibi, due_date: 2026-04-10, status: open; task: Confirm cabling work schedule with facilities team, owner: Abdullah Nouri, due_date: 2026-04-08, status: open

Next Meeting

The next meeting is scheduled for April 9, 2026, at 2:00 PM and will focus on the Requirements Sign-Off Review.

Notes

James will not be available on April 8; meetings should be scheduled to avoid this date. Ibrahim has requested that all technical specifications be shared at least 48 hours prior to the next session.