Meeting Info

meeting_title: Smart Building IoT System - Requirements Review; date: 2026-04-02; time: 2:00 PM; location: Virtual - Microsoft Teams; facilitator: Noura Al-Otaibi

Attendees

name: Noura Al-Otaibi, role: Project Manager; name: Ibrahim Qasim, role: IoT Solutions Architect; name: Fatima Al-Zahrani, role: Business Analyst; name: James Wilson, role: Vendor Technical Representative; name: Abdullah Nouri, role: Facilities Manager

Agenda

Review of draft requirements document; Vendor hardware compatibility discussion; Energy management module scope confirmation; Data privacy and compliance requirements; Risk review and mitigation strategies; Next steps and timeline confirmation

Discussion Summary

Noura initiated the session by reviewing the draft requirements document prepared by Fatima. Ibrahim identified that three proposed sensor types are incompatible with the current building network infrastructure and will require additional cabling work estimated at three weeks. James confirmed that the vendor can supply compatible alternative sensors with a lead time of six weeks from order placement. Abdullah stated that energy reporting is required to align with the Saudi Green Building Standard and requested its inclusion as a mandatory functional requirement. The team agreed that only anonymized, aggregated occupancy data will be collected in common areas to address data privacy concerns. Fatima noted that the current requirements document does not specify system behavior during network outages and requested Ibrahim to define the offline fallback behavior before the next meeting.

Decisions

Alternative sensor types from vendor approved subject to cost confirmation; Energy reporting module must comply with Saudi Green Building Standard; Occupancy tracking limited to anonymized aggregated data in common areas only; Offline fallback behavior to be defined and added to requirements before sign-off; Procurement process to start immediately to account for 6-week hardware lead time

Action Items

task: Update requirements document with Saudi Green Building Standard alignment, owner: Fatima Al-Zahrani, due_date: 2026-04-09, status: open; task: Define system offline fallback behavior specification, owner: Ibrahim Qasim, due_date: 2026-04-07, status: open; task: Submit hardware quotation for alternative sensor types, owner: James Wilson, due_date: 2026-04-06, status: open; task: Initiate procurement approval process for hardware order, owner: Noura Al-Otaibi, due_date: 2026-04-10, status: open; task: Confirm cabling work schedule with facilities team, owner: Abdullah Nouri, due_date: 2026-04-08, status: open

Next Meeting

The Requirements Sign-Off Review is scheduled for April 9, 2026, at 2:00 PM.

Notes

James will not be available on April 8, so all meetings are to be scheduled on alternative dates. Ibrahim requested that all technical specifications be distributed to participants at least 48 hours prior to the next session.