Meeting Info

meeting_title: Smart Building IoT System - Requirements Review; date: 2026-04-02; time: 2:00 PM; location: Virtual - Microsoft Teams; facilitator: Noura Al-Otaibi

Attendees

name: Noura Al-Otaibi, role: Project Manager; name: Ibrahim Qasim, role: IoT Solutions Architect; name: Fatima Al-Zahrani, role: Business Analyst; name: James Wilson, role: Vendor Technical Representative; name: Abdullah Nouri, role: Facilities Manager

Agenda

Review of draft requirements document; Vendor hardware compatibility discussion; Energy management module scope confirmation; Data privacy and compliance requirements; Risk review and mitigation strategies; Next steps and timeline confirmation

Discussion Summary

The discussion summary highlights the importance of aligning energy reporting with Saudi Green Building Standard requirements, which is now considered a mandatory functional requirement. The team also emphasized the need for anonymized aggregated data only to be collected in common areas regarding occupancy tracking sensors. Additionally, Ibrahim confirmed that three proposed sensor types are not compatible with the current building network infrastructure and would require additional cabling work estimated at 3 weeks. James further clarified that the vendor can supply compatible alternatives but lead time is 6 weeks from order placement. The team also discussed system behavior during network outages and agreed that offline fallback behavior needs to be defined before the next meeting, with Ibrahim tasked to address this requirement.

Decisions

Alternative sensor types from vendor approved subject to cost confirmation; Energy reporting module must comply with Saudi Green Building Standard; Occupancy tracking limited to anonymized aggregated data in common areas only; Offline fallback behavior to be defined and added to requirements before sign-off; Procurement process to start immediately to account for 6-week hardware lead time

Action Items

task: Update requirements document with Saudi Green Building Standard alignment, owner: Fatima Al-Zahrani, due_date: 2026-04-09, status: open; task: Define system offline fallback behavior specification, owner: Ibrahim Qasim, due_date: 2026-04-07, status: open; task: Submit hardware quotation for alternative sensor types, owner: James Wilson, due_date: 2026-04-06, status: open; task: Initiate procurement approval process for hardware order, owner: Noura Al-Otaibi, due_date: 2026-04-10, status: open; task: Confirm cabling work schedule with facilities team, owner: Abdullah Nouri, due_date: 2026-04-08, status: open

Next Meeting

The next meeting is scheduled for April 9, 2026 at 2:00 PM to review the requirements sign-off. This meeting will provide an opportunity to confirm the completeness and accuracy of the project's functional specifications prior to proceeding with development. The agenda will focus on finalizing the requirements documentation, addressing any outstanding questions or concerns, and ensuring a shared understanding among stakeholders.

Notes

James will not be available on April 8, and meetings should avoid that date to ensure his participation. Technical specifications are required to be shared at least 48 hours prior to the next session, as requested by Ibrahim.