Meeting Info

meeting_title: Smart Building IoT System - Requirements Review; date: 2026-04-02; time: 2:00 PM; location: Virtual - Microsoft Teams; facilitator: Noura Al-Otaibi

Attendees

name: Noura Al-Otaibi, role: Project Manager; name: Ibrahim Qasim, role: IoT Solutions Architect; name: Fatima Al-Zahrani, role: Business Analyst; name: James Wilson, role: Vendor Technical Representative; name: Abdullah Nouri, role: Facilities Manager

Agenda

Review of draft requirements document; Vendor hardware compatibility discussion; Energy management module scope confirmation; Data privacy and compliance requirements; Risk review and mitigation strategies; Next steps and timeline confirmation

Discussion Summary

Noura reviewed the draft requirements document prepared by Fatima, summarizing key points and highlighting areas for improvement. Ibrahim emphasized that three proposed sensor types are not compatible with the current building network infrastructure, requiring additional cabling work estimated at 3 weeks to implement. James confirmed that the vendor can supply compatible alternatives but lead time is 6 weeks from order placement. Abdullah stressed the importance of aligning energy reporting with Saudi Green Building Standard requirements and requested this be added as a mandatory functional requirement. The team agreed that anonymized aggregated data only will be collected in common areas for occupancy tracking sensors, addressing data privacy concerns. Fatima flagged that the current requirements document does not address system behavior during network outages and requested Ibrahim to define offline fallback behavior before the next meeting.

Decisions

Alternative sensor types from vendor approved subject to cost confirmation; Energy reporting module must comply with Saudi Green Building Standard; Occupancy tracking limited to anonymized aggregated data in common areas only; Offline fallback behavior to be defined and added to requirements before sign-off; Procurement process to start immediately to account for 6-week hardware lead time

Action Items

task: Update requirements document with Saudi Green Building Standard alignment, owner: Fatima Al-Zahrani, due_date: 2026-04-09, status: open; task: Define system offline fallback behavior specification, owner: Ibrahim Qasim, due_date: 2026-04-07, status: open; task: Submit hardware quotation for alternative sensor types, owner: James Wilson, due_date: 2026-04-06, status: open; task: Initiate procurement approval process for hardware order, owner: Noura Al-Otaibi, due_date: 2026-04-10, status: open; task: Confirm cabling work schedule with facilities team, owner: Abdullah Nouri, due_date: 2026-04-08, status: open

Next Meeting

The next meeting is scheduled for April 9, 2026 at 2:00 PM to review the requirements sign-off. The primary objective of this meeting is to ensure that all stakeholders are aligned on the project's scope and deliverables. A comprehensive review of the requirements documentation will take place during this session to confirm that all necessary details have been captured.

Notes

James' availability is subject to change, and he will not be available on April 8. Meetings should avoid scheduling conflicts with this date. All technical specifications are required to be shared at least 48 hours prior to the next session, as requested by Ibrahim.